## Sheet1
| Task Name | Difficulty | Duration | Start | Finish | Predecessors | Done
1 | Research repayment options, deferrment, refinance, etc | 8 | month (concurrent) | now | Dec 11 | none | 80%
2 | Buy domain name(s) | 1 |  | now | now | none | Done
3 | Set up website host. Integrate with GitHub. | 4 |  | Nov 15 | Dec 1 | 2 | 0%
4 | Build html form for inputting a loan | 7 | week | Dec 11 | Dec 18 | 3
5 | Build data handler | 5 | 3 days | Dec 17 | Dec 21
6 | submit button on input loan form - event handler | 4 | week | Dec 15 | Dec 25
7 | Build html form for inputting other info | 4 | 3 days | Dec 25 | Dec 29
8 | submit button on other info - event handler | 3 | week | Dec 26 | Jan 4
9 | Write a heuristic for scenarios | 9 | week | Jan 1 | Jan 11
10 | Write scenario generator | 8 | week | Jan 5 | Jan 18
11 | GUI to compare scenarios side by side | 7 | week+ | Jan 13 | Jan 27
12 | Plot amortization graph | 6 | week | Jan 23 | Feb 3
13 | Write informative text, how loans work | 3 | week | Feb 1 | Feb 10
14 | Polish website and publish it. Advertize on subreddit, etc | 6 | 3 days | Feb 5 | Feb 13
15 | Extra time - buffer |  | month+ | Feb 13 | April 1
16
17
18
19
20
21
22